## Slide 1
Build Status Update
Where we are.
What's left.
Internal review · April 2026

## Slide 2
Where we are, in one frame
Four areas of work, each tracking against a definition of done.
2 / 10
Customer-facing site
9 of 9 pages live, including member area
90%
Admin console
8 modules + Settings + Help wired
85%
Auth & member experience
Login, JWT, role gating, dashboard — done
95%
Backend API
Foundation + 6 routes; payments TBD
60%

## Slide 3
Backend foundation
Industrial Express + SQLite layout. Clean module boundaries; one source of truth per concern.
3 / 10
C
config/
Typed env loader, business constants, CORS policy
D
db/
12 SQL migrations + runner + seed + WAL connection
M
middleware/
asyncHandler, validate, auth, requestId, audit
S
services/
9 services — pricing canonical, the rest skeletons
R
routes/
9 route groups; /api/auth and /api/bookings live
U
utils/
errors, ids (crypto), money, phone (GH), dates, logger
Numbers, not vibes
Counted from /backend after the restructure.
12
Migrations
Indexed, FK-on, transaction-wrapped
9
Services
Pricing canonical; payments/SMS skeletons
8
Middleware
incl. fire-and-forget audit
13
DB tables
users, bookings, payments, audit_log, plus more
1×
Quote calc
Frontend + backend share the same formula

## Slide 4
Customer-facing site — pages live
Nine pages share one nav/footer mount, one stylesheet, one auth widget.
4 / 10
Home
Hero, trust bar, service tiles
Services
Residential, commercial, decorative
Get a quote
Instant pricing in under 3 sec
Booking
Calendar, payment select, confirm
Track project
Live stages, ETA, contact master
MEMBER ONLY
Our Masters
Browse painters by region + rating
About
Story, warranty policy, contact
Sign in
Unified login for 3 roles
My account
Bookings, warranty, profile, sign out
MEMBER ONLY

## Slide 5
Admin console — eight modules wired
Dispatcher view of the whole operation. Settings + Help added this sprint.
5 / 10
D
Dashboard
Revenue chart, today's schedule
J
Job Board
Kanban across 6 stages
M
Paint Masters
Roster, ratings, filters
C
Customers
CRM: LTV, history, notes
I
Inventory
Stock + low-reorder alerts
A
Analytics
Revenue mix, funnel, top performers
S
Settings
Branding, pricing, security
H
Help & Support
FAQ, contact, ticket form

## Slide 6
Auth & member experience
One login form, three roles, a /next= redirect that brings members back.
6 / 10
login.html
Phone + password
Unified form, role pills
/api/auth/login
Backend verifies
Falls back to demo creds
JWT issued
localStorage
pmAuth.user() reads it
Role check
admin / customer / painter
pmRequireAuth gates
→ Customer
my.html — bookings, warranty, profile
→ Paint Master
index.html (dashboard on roadmap)
→ Admin
admin/index.html — full console
What this gives us, beyond a login screen
•
Single source of truth — pmRequireAuth() gates any future page in one line
•
Round-trip redirect — ?next= remembers where the member was headed and returns them after sign-in
•
Open-redirect safe — same-origin paths only; absolute and protocol-relative URLs are rejected
•
Demo credentials baked in — flow works without the API; switches to real backend automatically

## Slide 7
Brand system — one mark, four contexts
Drop a logo file once; nav, footer, sidebar, login all pick it up via CSS variables.
7 / 10
PAINT
MASTERS
Customer nav
Light surface · dark mark
PAINT
MASTERS
Customer footer
Dark surface · light mark
PAINT
MASTERS
Admin sidebar
Dark surface · light mark
Login hero
Dark surface · full lockup
Why it's dynamic, not just "we put the file there"
•
Four asset variants (mark/lockup × dark/light) generated automatically from one upload
•
CSS :has(img) drops the placeholder navy box the moment a real image is present
•
--brand-mark-size + .lg/.xl/.xxl modifiers — same logo at 34px in nav, 120px in Settings preview
•
Missing-file safety: every brand mark falls back to "PM" text rather than a broken image

## Slide 8
Milestones reached this sprint
Each marker = a complete, verifiable deliverable.
8 / 10
Apr 24
Backend audit + hygiene fixes
Apr 25
Foundation config/utils/middleware
Apr 25
DB layer + 12 migrations
Apr 25
Services pricing canonical
Apr 26
Admin Settings + Help wired
Apr 26
Logo system + favicon
Apr 27
Member experience + /api login
TODAY

## Slide 9
What's next — prioritised
Three buckets. P0 unblocks a real customer. P1 makes the platform investable.
9 / 10
P0
Ship blockers
Wire Paystack for real payment capture + webhook
MoMo payout flow for paint masters (24h SLA)
Hubtel SMS for booking + dispatch alerts
Smoke test the API end-to-end on a host with npm
Replace localStorage seed data with real /api fetches
P1
Next sprint
Painter dashboard (separate from customer my.html)
Admin: real analytics tied to bookings table
Quote → booking conversion + contract PDF render
Inventory write-paths (suppliers, POs, usage)
Forgot-password flow + email verification
P2
Later
Twi translations (lang toggle is stubbed)
WhatsApp channel via Hubtel
Mobile-app shell around the same backend
Reviews moderation queue in admin
Multi-region rollout (Kumasi, Tema, Cape Coast)

## Slide 10
Risks & open questions
What's not done. What I'm uncertain about. Where I need a co-founder call.
10 / 10
Risk
Payments not yet executing money
Gateway functions are stubbed; real transactions move through Paystack only when keys are wired and the webhook is verified.
Risk
Frontend still on localStorage seed data
Customer + admin pages read from localStorage, not the API. Demo accounts work; any real booking would not persist.
Risk
API smoke test never run from this sandbox
Backend code is syntax-clean but the npm registry is blocked here, so I haven't booted the server. Needs a host with internet to verify.
Decision
Are we shipping a painter dashboard or skipping?
Currently painters land on the customer site after sign-in. Decide: minimum painter view or punt to v2?
Decision
Single-admin model — how do we add more?
create-admin script exists but no UI. Comfortable with shell access for now, or build admin invite flow?
Open Q
12-month warranty — who pays for rework?
Code tracks the certificate; financial liability needs a policy + reserve. Worth a separate call.